## Slide 1: India Routine Immunization & Measles SIA synergies assessment
Dr. Satish Gupta
Measles Rubella Initiative Meeting
18-19 September 2012
Washington DC

## Slide 2: The India Measles SIA
India Technical advisory group on immunizations endorses the following
  Delivery of second dose of measles vaccine should be via SIA in states with MCV1 coverage <80%
Phase 1 SIA
  “Pilot” phase
  5-10 districts in selected states conducted the SIA
  SIA Phase 1 timing: November 2010 to June 2011

## Slide 3: SIA implementation
Health worker training
  Occurred 2-3 weeks prior to SIA dates
Length of time to conduct SIA
  3 weeks (2 weeks from fixed locations and 1 week within schools)
SIA monitoring
  Conducted by National Polio Surveillance Project (NPSP), UNICEF, other organizations

## Slide 4: Measles SIA – routine immunization synergies assessment
Assessment objective
  Determine the impact of conducting the SIA on the status of routine immunization (RI) services
Assessment partners
  GOI, UNICEF, NPSP, MCHIP & CDC
Assessment methods
  Repeatedly measure RI process indicators in 20 selected facilities before, during and after the Phase 1 SIA

## Slide 5: Assessment Methods
Location
  5 Measles SIA Phase-1 districts of Jharkhand state
Data collection method
  UNICEF, MCHIP, NPSP & CDC surveyors conducted health facility staff interviews, record reviews and observations during RI sessions; interviews with district staff
When interviews were conducted
  Before campaign: January 2011
  During campaign: March 2011
  After campaign: November 2011
Same 20 facilities visited each time

## Slide 6: Topics covered in assessment tools
Training received on various RI topics
Knowledge of
  measles and measles vaccination
  AEFIs
Existence of
  Routine immunization microplans, maps, waste management equipment
Supervisory practices
Vaccination session practices including
  Injection safety
  Vaccine handling
  Waste management
  Documentation
  Messages to beneficiaries
Number of routine DTP1 and DTP3 doses administered monthly before and after campaign

## Slide 7: Data Analysis
Measure any significant changes over time
  For indicators which were collected before/during/after or before/after SIA, paired t-tests were used to measure significance
Analysis software: SAS 9.3

## Slide 8: Results: Indicators which changed significantly* before versus after SIA
Category | Indicator | Before SIA | After SIA
Vaccine safety | Health worker knows a child with AEFI should be given first aid; referred | 70% | 100%
 | Health worker has AEFI contact information | 65% | 85%
 | Health worker has working hub cutter | 80% | 100%
 | Health worker kept Measles vial in hole of ice pack during RI session | 20% | 55%
Record-keeping | Health worker properly filled register, health card, tally at RI session | 52% | 84%
Cold chain | Health worker received cold chain training past 6 months | 25% | 58%
Waste mgmt | Health worker received waste management training in past 6 months | 45% | 74%
Child tracking | Health worker received training on child tracking in past 6 months | 20% | 42%

## Slide 9: Results: Indicators with high values before SIA which did not significantly change after SIA
Cat-egory | Indicator | Before SIA | After SIA
Vacc-ination eligibility | HW knows infants who just received Measles RI dose is eligible for measles SIA dose | 95% | 95%
 | HW knows correct measles vaccine contraindications | 85% | 90%
Waste mgmt | Waste management bags available at RI session | 85% | 95%
Vaccine handling | Vials at session have properly marked reconstitution information (date, time) | 87% | 95%
 | No expired vaccine found at RI session | 100% | 100%
 | Correct diluent used for MCV or BCG vaccines at session | 100% | 100%
Injection safety | During injection, HW did not touch needle | 90% | 90%
 | Hub cutter used to cut used syringe during RI session | 90% | 90%
 | HW used correct route of injection during RI session | 90% | 90%
AEFI | HW know AEFI management center location | 75% | 90%
High values defined as greater than 75%

## Slide 10: Results: Indicators with low values before SIA which did not significantly change after SIA
Cat-egory | Indicator | Before SIA | After SIA
Planning | Health worker received target population training in past 6 months | 20% | 30%
 | Facility catchment map available | 20% | 20%
 | Facility microplan available | 35% | 50%
Supervision | Supervisory visit documentation available | 15% | 35%
AEFIs | Beneficiary told about possible AEFIs and who to contact | 39% | 32%
Low values defined as less than 40%

## Slide 11: Conclusions: Observed strengths
Significant improvements seen in some indicators after the SIA including
  Certain AEFI knowledge,
  Some vaccine handling practices,
  Recording practices
Many areas were strong prior to SIA and remained strong including
  most vaccine handling and safe injection practices,
  knowledge of infant eligibility for vaccination

## Slide 12: Conclusions: Observed Challenges
SIA tools and information (example: SIA microplan) infrequently used to improve RI
Many areas were weak prior to SIA and remained weak after SIA including:
  Weak availability of RI microplans and maps,
  Weak supervision
No change in multiple indicators including:
  Dropout rates,
  Number of doses administered,
  Conducting RI sessions during the SIA

## Slide 13: Recommendations
Some RI indicators may be easier to impact by SIAs
  Measles SIAs may be able to make a realistic impact on highly overlapping routine immunization topics such as health worker knowledge of adverse events and vaccine handling
Other RI indicators may be too constrained
  Certain RI activities may be hampered by other systematic issues and not possible to positively impact (i.e. RI supervision may not have changed due to lack of funds for transport)
Synergy focal points are needed throughout the SIA process
  A “champion” focused on actively ensuring routine immunization strengthening activities occurs during the Measles SIA may be critical to ensuring opportunities for synergy are acted upon

## Slide 14
Thank You
You got it!